## Feature Matrix
Doppio — Detailed Feature & Task Matrix
Doppio — your AI double that listens & remembers, in Bangla ¦ Task-list-ready breakdown ¦ Initial → MVP → V1 → V2 → V3 (North-Star)
ID | Phase | Epic | Feature | Task | User Story | Acceptance Criteria | Persona | Target User | Component | Dependencies | Priority | Effort
INIT-01 | Initial | Onboarding & Account | Phone / Email OTP sign-up | Phone + OTP auth flow | As a user, I want to sign up with my phone number and an OTP so I can start without a card. | SMS OTP delivered <30s; resend & retry; session token issued; invalid/expired OTP handled. | User | All | Backend, Mobile | — | P0 | M
INIT-02 | Initial | Onboarding & Account | Phone / Email OTP sign-up | Email sign-up fallback | As a user, I want an email option in case SMS fails. | Email + verification link; duplicate-account prevention; merges to one identity. | User | All | Backend, Mobile | INIT-01 | P1 | S
INIT-03 | Initial | Onboarding & Account | Bangla / English UI toggle | i18n localization framework | As a user, I want the interface in Bangla so I can navigate comfortably. | All strings externalized; language switch persists; Bangla webfont renders on all devices. | User | All | Mobile, Chrome | — | P0 | M
INIT-04 | Initial | Onboarding & Account | Bangla / English UI toggle | Bangla translation pass | As a user, I want correct, natural Bangla copy. | 100% of MVP screens translated and reviewed by a native speaker. | User | All | Design | INIT-03 | P0 | S
INIT-05 | Initial | Onboarding & Account | Guided first-run walkthrough | Onboarding + permission primers | As a user, I want a short walkthrough so I know how to record and read notes. | Mic-permission primer; 3–4 skippable slides; shown once; re-openable from settings. | User | All | Mobile | INIT-03 | P1 | S
INIT-06 | Initial | Audio Capture | In-person mobile recording | Mic capture + recording controls | As a user, I want to record a live lecture or conversation on my phone. | Start/stop; live level meter; handles incoming-call interruption; autosave on crash. | User | Student, Doctor | Mobile | — | P0 | M
INIT-07 | Initial | Audio Capture | In-person mobile recording | Audio chunking pipeline | As the system, I want audio chunked for streaming transcription. | Gapless chunks; ordered upload/queue; resilient to network drop. | System | All | Mobile, Backend | INIT-06 | P0 | M
INIT-08 | Initial | Audio Capture | Background + low-battery recording | Background recording service | As the system, I want recording to continue in the background efficiently. | Continues screen-off/backgrounded; survives 12h; battery drain within target/hr. | System | All | Mobile | INIT-06 | P0 | L
INIT-09 | Initial | Audio Capture | Pause / resume recording | Pause/resume control + state | As a user, I want to pause to skip private moments. | Paused audio excluded; seamless resume; clear paused indicator. | User | All | Mobile | INIT-06 | P1 | S
INIT-10 | Initial | Transcription (Core) | Bangla speech-to-text engine | STT approach eval (build vs API) | As the system, I want the best Bangla STT path chosen on evidence. | Benchmark WER on Bangla test set; build-vs-API decision; unit-cost model documented. | System | All | ML-STT | — | P0 | XL
INIT-11 | Initial | Transcription (Core) | Bangla speech-to-text engine | Bangla STT inference service | As a user, I want my Bangla speech transcribed accurately. | Streaming + batch modes; <2x real-time; WER target met; horizontally scalable. | System | All | ML-STT, Backend | INIT-10 | P0 | XL
INIT-12 | Initial | Transcription (Core) | Bangla speech-to-text engine | Dialect, punctuation & numerals | As the system, I want common accents and formatting handled. | Common regional accents handled; auto-punctuation; Bangla numerals & dates. | System | All | ML-STT | INIT-11 | P1 | L
INIT-13 | Initial | Transcription (Core) | Bangla–English code-switch | Code-switch language model | As the system, I want mixed Bangla-English speech transcribed correctly. | Mixed utterances transcribed; English technical terms preserved; consistent script. | System | Professional, Doctor | ML-STT | INIT-11 | P0 | L
INIT-21 | Initial | Transcription (Core) | Bangla quality gate | Bangla quality benchmark & release gate | As the system, I want Bangla quality measured against a fixed bar so it ships only when it is genuinely good. | Curated Bangla + code-switch test set; WER & summary-quality thresholds defined as a release gate; tracked every build. | System | All | ML-STT, AI-LLM | INIT-11, INIT-13 | P0 | M
INIT-14 | Initial | Transcription (Core) | Live transcript view | Real-time transcript UI | As a user, I want to see the transcript appear live to confirm capture. | Latency <1.5s; partial→final tokens; auto-scroll; timestamps. | User | All | Mobile | INIT-11 | P1 | M
INIT-15 | Initial | Data & Storage | Local-first storage | On-device encrypted store | As the system, I want recordings stored on-device by default. | Encrypted at rest; survives restart; storage-quota management & cleanup. | System | All | Mobile | — | P0 | M
INIT-16 | Initial | Data & Storage | Recording / session list | Session list + detail screen | As a user, I want a list of past recordings so I can find them later. | Sorted by date; title search; opens to transcript/notes/summary. | User | All | Mobile | INIT-15 | P0 | M
INIT-17 | Initial | Data & Storage | Recording / session list | Delete / rename session | As a user, I want to rename or delete sessions. | Delete with confirm; rename persists; reflected in search. | User | All | Mobile | INIT-16 | P1 | S
INIT-18 | Initial | Privacy & Security | On-device transcription (no audio retention) | Private mode | As the system, I want audio discarded after transcription for sensitive use. | Toggle; audio never uploaded; only transcript stored; clearly indicated in UI. | System | Doctor | Mobile, ML-STT | INIT-11, INIT-15 | P0 | M
INIT-19 | Initial | Platform Foundation | Core backend | Auth / identity + API gateway | As the system, I want a secure backend foundation. | JWT auth; rate limiting; versioned secure endpoints; secrets management. | System | All | Backend, Infra | — | P0 | L
INIT-20 | Initial | Platform Foundation | Core infra | CI/CD, environments, monitoring | As the system, I want reliable deploy & observability. | Staging + prod; deploy pipeline; centralized logging, metrics & alerting. | System | All | Infra | — | P0 | L
MVP-01 | MVP | AI Notes & Summaries | Auto session summary | Summarization pipeline | As the system, I want a summary generated after each session. | Summary within target time; sections (overview/decisions/next steps); Bangla & English. | System | Professional, Doctor | AI-LLM, Backend | INIT-11 | P0 | L
MVP-02 | MVP | AI Notes & Summaries | Auto session summary | Prompt + output templates | As the system, I want consistent, cost-tracked summary structure. | Standard template; token cost logged; configurable length. | System | All | AI-LLM | MVP-01 | P0 | M
MVP-03 | MVP | AI Notes & Summaries | Auto session summary | Summary view + regenerate | As a user, I want to read, copy and regenerate the summary. | View; regenerate; copy-to-clipboard; loading & error states. | User | All | Mobile, Chrome | MVP-01 | P1 | S
MVP-04 | MVP | AI Notes & Summaries | Action item extraction | To-do extraction | As the system, I want action items pulled automatically. | Items with owner/date where stated; editable; deduped. | System | Professional | AI-LLM | MVP-01 | P0 | M
MVP-05 | MVP | AI Notes & Summaries | Action item extraction | To-do management UI | As a user, I want to manage extracted tasks. | Check off; edit; aggregated tasks view across sessions. | User | Professional | Mobile | MVP-04 | P1 | M
MVP-06 | MVP | AI Notes & Summaries | Editable notes | Inline note editor | As a user, I want to add my own notes alongside the transcript. | Add/edit during & after; autosave; notes linked to timestamps. | User | Student | Mobile | INIT-14 | P1 | M
MVP-07 | MVP | AI Notes & Summaries | Auto title & tagging | Auto-title + topic tags | As the system, I want sessions auto-titled and tagged. | Title generated; 3–5 tags; user-editable; used in search. | System | All | AI-LLM | MVP-01 | P1 | S
MVP-08 | MVP | Memory & Search | Keyword search | Full-text search index | As a user, I want to search all my notes by keyword. | Indexes transcript+notes+title; Bangla tokenization; ranked results. | User | Journalist | Backend | INIT-16 | P0 | M
MVP-09 | MVP | Memory & Search | Keyword search | Search UI + filters | As a user, I want to filter and see matches highlighted. | Query box; date/type filters; match highlighting. | User | All | Mobile, Chrome | MVP-08 | P1 | S
MVP-10 | MVP | Memory & Search | Ask Doppio | RAG over single session | As a user, I want to ask questions about a meeting. | Grounded answer; cites timestamps; Bangla & English Q&A. | User | All | AI-LLM, Backend | MVP-01 | P0 | L
MVP-11 | MVP | Memory & Search | Ask Doppio | Chat UI | As a user, I want a conversational way to query a session. | Threaded chat; follow-ups; copy answer; empty/error states. | User | All | Mobile, Chrome | MVP-10 | P1 | M
MVP-12 | MVP | Capture Expansion | Chrome extension | Extension scaffold + tab audio capture | As a user, I want to capture Zoom/Meet calls from my browser. | Captures tab audio on Meet/Zoom web; start/stop; permission flow. | User | Professional | Chrome | INIT-07 | P0 | L
MVP-13 | MVP | Capture Expansion | Chrome extension | Extension transcript/summary panel | As a user, I want live transcript and summary in the browser. | Side-panel live transcript; summary after; links to web app. | User | Professional | Chrome | MVP-12, MVP-01 | P0 | M
MVP-14 | MVP | Capture Expansion | Quick voice note | One-tap voice memo | As a user, I want quick voice memos transcribed. | Record from home screen; transcribed; saved as a session. | User | Journalist | Mobile | INIT-06 | P1 | S
MVP-15 | MVP | Monetization & Payments | Free tier | Usage metering + caps | As the system, I want to meter usage and enforce free limits. | Track minutes/AI calls; enforce free cap; show usage to user. | System | All | Backend | INIT-19 | P0 | M
MVP-16 | MVP | Monetization & Payments | Pro subscription | Plans + entitlements | As the system, I want plans that gate features. | Monthly ৳200–300; entitlement gates; grace period & expiry handling. | System | All | Backend | MVP-15 | P0 | M
MVP-17 | MVP | Monetization & Payments | bKash / Nagad / Rocket | bKash integration | As a user, I want to pay with bKash since I have no card. | Checkout; webhook confirms payment; renewal; failure/refund handling. | User | All | Payments, Backend | MVP-16 | P0 | L
MVP-18 | MVP | Monetization & Payments | bKash / Nagad / Rocket | Nagad + Rocket integration | As a user, I want more MFS payment options. | Both gateways live; unified receipt & reconciliation. | User | All | Payments, Backend | MVP-17 | P1 | M
MVP-19 | MVP | Monetization & Payments | In-app subscription mgmt | Manage / cancel / upgrade | As a user, I want to manage my plan in-app. | See current plan; upgrade/downgrade; cancel; invoice history. | User | All | Mobile | MVP-16 | P1 | M
MVP-20 | MVP | Sync & Platform | Cross-surface sync (web · mobile · Chrome) | Cloud sync service | As the system, I want sessions synced across the web portal, mobile and the Chrome extension. | Two-way sync across all surfaces; conflict resolution; offline queue & retry. | System | Professional | Backend | INIT-15, INIT-19 | P0 | L
MVP-21 | MVP | Sync & Platform | iOS app | iOS parity build | As a user, I want the app on iPhone too. | Capture/transcript/notes/summary parity; background recording within iOS limits. | User | All | iOS | INIT-06, INIT-11, MVP-01 | P0 | XL
MVP-22 | MVP | Sync & Platform | Encrypted cloud backup | Optional encrypted backup | As a user, I want optional backup so I don't lose notes. | Opt-in; encrypted; restore on a new device. | User | All | Backend, Mobile | MVP-20 | P1 | M
MVP-23 | MVP | Sharing & Export | Share summary | Share to WhatsApp / link | As a user, I want to share a summary via WhatsApp. | Share as text or link; link access control; expiry option. | User | Professional | Mobile, Backend | MVP-01 | P0 | S
MVP-24 | MVP | Sharing & Export | Export PDF / Word | Export transcript + summary | As a user, I want to export to share with others. | PDF & DOCX; Bangla font embedded; includes notes & action items. | User | Journalist | Mobile, Backend | MVP-01 | P1 | M
MVP-25 | MVP | Localization & Access | Data-light mode | Bandwidth optimization | As the system, I want low data usage on mobile networks. | Compressed uploads; toggle; usable on 2G/3G. | System | All | Mobile, Backend | MVP-20 | P1 | M
MVP-26 | MVP | Localization & Access | Offline transcription | On-device offline STT model | As the system, I want transcription to work offline. | Smaller on-device model; queues & syncs results when online. | System | All | ML-STT, Mobile | INIT-11 | P2 | XL
MVP-27 | MVP | AI Quality | Bangla AI-quality validation | Validate summaries / action items / Q&A on Bangla | As the system, I want the AI layer proven on Bangla, not just English. | Summaries, action items & Q&A evaluated on real Bangla + code-switch sessions; quality bar met before launch. | System | All | AI-LLM | MVP-01, MVP-04, MVP-10 | P0 | M
MVP-28 | MVP | Web Portal | Web app shell & auth | Responsive web portal + sign-in | As a user, I want a web portal where I sign in and reach everything. | Responsive layout; OTP/email sign-in; top nav (Home, Library, Search, Settings); session persistence. | User | All | Web, Backend | INIT-19 | P0 | L
MVP-29 | MVP | Web Portal | Session library | Web library & dashboard | As a user, I want all my sessions in one place on the web. | Lists & filters all sessions; recents on the dashboard; opens to a session. | User | All | Web | MVP-28, INIT-16 | P0 | M
MVP-30 | MVP | Web Portal | Session workspace | Web transcript / summary / notes view | As a user, I want to read, edit and play back a session in the portal. | Transcript + summary + notes; edit notes; regenerate summary; audio playback synced to transcript. | User | All | Web | MVP-28, MVP-01, MVP-06 | P0 | L
MVP-31 | MVP | Web Portal | Search & Ask on web | Web search + Ask Doppio | As a user, I want to search and ask questions about my sessions in the portal. | Full-text search with filters; Ask Doppio chat; grounded answers with timestamps. | User | All | Web | MVP-08, MVP-10, MVP-28 | P1 | M
MVP-32 | MVP | Web Portal | Account & billing | Web subscription & billing centre | As a user, I want to manage my plan and payments on the web. | View/upgrade/cancel plan; bKash/Nagad/Rocket; invoice history; usage meter. | User | All | Web, Payments | MVP-16, MVP-28 | P0 | M
MVP-33 | MVP | Web Portal | Settings & privacy | Web settings & privacy controls | As a user, I want to manage language, privacy and data from the portal. | Language toggle; private mode; profile; data export & account deletion. | User | All | Web | MVP-28 | P1 | M
MVP-34 | MVP | Web Portal | Export & share | Web export & share | As a user, I want to export and share sessions from the portal. | Export PDF/DOCX; share link or WhatsApp; access controls on shared links. | User | All | Web | MVP-23, MVP-24, MVP-28 | P1 | S
MVP-35 | MVP | Import & Memory | File upload | Audio/video upload → transcribe & summarize | As a user, I want to upload existing recordings and have them transcribed into memory. | Accepts mp3/wav/m4a/mp4; runs standard pipeline; counts against usage; progress + error states. | User | All | Web, Mobile, Backend, ML-STT | INIT-11, MVP-01, MVP-15 | P1 | M
MVP-36 | MVP | Import & Memory | Share-to-Doppio | WhatsApp / share-sheet voice-note import | As a user, I want to forward a voice note straight into Doppio. | Appears in OS share sheet; imports audio; becomes a session. | User | All | Mobile | MVP-35 | P1 | S
MVP-37 | MVP | Import & Memory | Text import | Transcript / text-note import | As a user, I want to bring in an existing transcript or notes as a session. | Paste or upload text; stored & indexed as a session. | User | Journalist | Web, Backend | INIT-16 | P2 | S
V1-01 | V1 | Content Generation | Generate docs | Content-generation engine | As a user, I want documents generated from my notes. | Pick template; generate from session; edit & export; Bangla/English. | User | Student | AI-LLM | MVP-01 | P1 | M
V1-02 | V1 | Content Generation | Generate docs | Study guide / email / MoM formats | As a user, I want ready-made formats for my use cases. | Study guide, follow-up email, minutes formats; editable. | User | Student, Professional | AI-LLM | V1-01 | P1 | M
V1-03 | V1 | Content Generation | Domain templates | SOAP / minutes / interview templates | As a user, I want structured output for my field. | Domain-specific structure (e.g. doctor SOAP); editable; saved presets. | User | Doctor | AI-LLM | V1-01 | P1 | M
V1-04 | V1 | Content Generation | Auto-translate | Bangla ↔ English translation | As the system, I want summaries/transcripts translated. | Toggle language; acceptable quality; preserves key terms. | System | Professional | AI-LLM | MVP-01 | P1 | M
V1-05 | V1 | Deep Memory | Deep search across meetings | Cross-session RAG | As a user, I want to ask questions across all meetings. | Answers span sessions; cite source meeting; Bangla & English. | User | All | AI-LLM, Backend | MVP-10 | P1 | L
V1-06 | V1 | Deep Memory | Deep search across meetings | Bangla vector index | As the system, I want embeddings for Bangla retrieval. | Bangla embeddings; incremental indexing; relevance tuned. | System | All | ML, Backend | V1-05 | P1 | L
V1-07 | V1 | Deep Memory | Proactive suggestions | Live suggestion engine | As the system, I want relevant context surfaced live. | Surfaces related past context during a meeting; opt-in; low latency. | System | Professional | AI-LLM | MVP-10 | P2 | L
V1-08 | V1 | Integrations | Google Calendar sync | Calendar OAuth + event import | As the system, I want meetings detected from the calendar. | Connect Google; auto-create sessions from events; pre-meeting reminder. | System | Professional | Backend | INIT-19 | P1 | M
V1-09 | V1 | Integrations | Meeting bot | Zoom/Meet/Teams join-bot | As a user, I want a bot to join and record calls. | Bot joins via link; records; posts transcript & summary back. | User | Professional | Backend, Infra | MVP-01 | P1 | XL
V1-10 | V1 | Integrations | Gmail follow-up | Gmail send integration | As a user, I want generated follow-ups ready in Gmail. | Connect Gmail; create draft or send generated follow-up. | User | Professional | Backend | V1-01 | P2 | M
V1-11 | V1 | Collaboration | Shared workspaces | Teams / workspaces + roles | As a user, I want shared folders for my team. | Create team; invite members; shared session folders; permissions. | User | Professional | Backend | MVP-20 | P1 | L
V1-12 | V1 | Collaboration | Shared workspaces | Workspace UI | As a user, I want to switch between personal and team spaces. | Workspace switcher; shared session list; member visibility. | User | Professional | Mobile, Chrome | V1-11 | P1 | M
V1-13 | V1 | Collaboration | Comments & highlights | Transcript annotation | As a user, I want to highlight and comment on the transcript. | Highlight text; threaded comments; @mention; resolve. | User | Journalist | Mobile, Backend | V1-11 | P2 | M
V1-14 | V1 | Collaboration | Speaker identification | Diarization pipeline | As the system, I want to label who said what. | Separates speakers; rename labels; works on Bangla audio. | System | All | ML, Backend | INIT-11 | P1 | L
V1-15 | V1 | Monetization | Team / SME plans | Team billing + seats | As an admin, I want a team plan with central billing. | Per-seat pricing; central invoice; bKash/card; add/remove seats. | Admin | Professional | Payments, Backend | MVP-16, V1-11 | P1 | M
V1-16 | V1 | Monetization | Student discount | Student verification tier | As a user, I want a discounted student plan. | Verify student email/ID; discounted plan applied; periodic re-verify. | User | Student | Backend | MVP-16 | P2 | S
V1-17 | V1 | Web Portal | Workspace admin | Web workspace & member management | As an admin, I want to manage my team, roles and shared folders from the portal. | Invite/remove members; assign roles; manage shared folders; web-first admin. | Admin | Professional | Web, Backend | V1-11 | P1 | M
V1-18 | V1 | Web Portal | Integrations hub | Web integrations management | As a user, I want to connect and manage integrations from the portal. | Connect/disconnect Calendar, Gmail & meeting bot; show status & re-auth. | User | Professional | Web | V1-08, V1-09, V1-10 | P2 | S
V1-19 | V1 | Import & Memory | Document to memory | Document upload (PDF/DOCX/image OCR) | As a user, I want to add documents to memory so search & Ask can use them. | PDF/DOCX/image OCR; chunked & indexed; appears in deep search & Ask Doppio. | User | All | Web, Backend, AI-LLM, ML | V1-05, V1-06 | P1 | L
V1-20 | V1 | Import & Memory | Bulk import | Bulk / folder import & migration | As a user, I want to import many files at once, incl. from other note apps. | Multi-file upload; maps other tools' exports; batch status. | User | All | Web, Backend | MVP-35 | P2 | M
V1-21 | V1 | Import & Memory | Link ingestion | Link / article ingestion | As a user, I want to drop a URL/article into memory. | Fetches & extracts article; indexed for search & Ask. | User | Journalist | Web, Backend, AI-LLM | V1-06 | P2 | M
V2-01 | V2 | Second Brain | Daily / weekly digest | Digest generation + delivery | As the system, I want to compile a digest of meetings & tasks. | Scheduled digest; push/email; Bangla; user-set cadence. | System | Professional | AI-LLM, Backend | V1-05 | P2 | M
V2-02 | V2 | Second Brain | Cross-meeting insights | Theme / connection detection | As the system, I want to connect themes across sessions. | Surfaces recurring themes, people & open threads across meetings. | System | Journalist | AI-LLM | V1-05 | P2 | L
V2-03 | V2 | Advanced AI | Multi-LLM choice | Model selector + routing | As a user, I want to choose the AI model. | Choose Claude/GPT/Gemini; per-task default; relative cost shown. | User | Professional | AI-LLM, Backend | MVP-02 | P2 | M
V2-04 | V2 | Advanced AI | Custom AI assistants | Assistant / persona builder | As a user, I want a domain-tuned assistant. | Create assistant with custom instructions; reuse across sessions. | User | Doctor | AI-LLM | V2-03 | P2 | L
V2-05 | V2 | Advanced AI | Live translated captions | Real-time translation overlay | As the system, I want live translated captions. | Live captions translated; <2s latency; bilingual meeting support. | System | All | AI-LLM, ML | V1-04 | P2 | XL
V2-06 | V2 | Vertical – Healthcare | EMR-ready clinical note export | Structured clinical export | As a user, I want consult notes formatted for EMR import. | Export to EMR/FHIR or Niramoy format; field mapping; validation. | User | Doctor | Backend | V1-03 | P2 | L
V2-07 | V2 | Vertical – Healthcare | Medical dictionary | Bangla/English medical lexicon | As the system, I want accurate medical-term transcription. | Medical terms, drug names & abbreviations recognized; custom lexicon. | System | Doctor | ML-STT | INIT-13 | P2 | M
V2-08 | V2 | Vertical – Education | Lecture → quiz / flashcards | Quiz / flashcard generator | As a user, I want quizzes generated from lectures. | Generate MCQ & flashcards from a lecture; export/share. | User | Student | AI-LLM | V1-01 | P2 | M
V2-09 | V2 | Enterprise & Admin | Admin dashboard | Usage analytics dashboard | As an admin, I want analytics across my team. | Per-team usage, minutes, active users; CSV export. | Admin | Professional | Backend, Web | V1-15 | P2 | L
V2-10 | V2 | Enterprise & Admin | SSO & RBAC | SSO + role-based access | As an admin, I want SSO and access roles. | SSO (Google/SAML); role-based permissions; audit log. | Admin | Professional | Backend, Infra | V1-11 | P2 | L
V2-11 | V2 | Enterprise & Admin | Data residency | In-country hosting option | As an admin, I want data stored in-country for compliance. | Data stored in BD region; compliance documentation provided. | Admin | Doctor | Infra | INIT-20 | P2 | L
V2-12 | V2 | Enterprise & Admin | Retention policy | Configurable retention controls | As an admin, I want to set retention & deletion rules. | Set retention period; auto-delete; legal-hold override. | Admin | Professional | Backend | INIT-15 | P2 | M
V2-13 | V2 | Ecosystem | Public API / webhooks | Developer API + webhooks | As an admin, I want API access to integrate Doppio. | API keys; docs; webhook events; per-key rate limits. | Admin | Professional | Backend | INIT-19 | P2 | L
V2-14 | V2 | Ecosystem | Referral program | Referral / affiliate system | As a user, I want to refer friends for rewards. | Referral codes; reward credit; attribution tracking. | User | All | Backend | MVP-16 | P2 | M
V3-01 | V3 | Lang Depth · Dialects | Regional dialect STT | Dialect-adaptive Bangla models | As a user, I want my regional dialect (Sylheti, Chittagonian, etc.) transcribed accurately. | Major dialects detected & transcribed; graceful fallback to standard Bangla; per-dialect WER targets. | System | All | ML-STT | INIT-11, INIT-13 | P1 | XL
V3-02 | V3 | Lang Depth · Dialects | Regional dialect STT | Dialect auto-detection | As the system, I want to detect the speaker's dialect and switch models automatically. | Detects dialect within first utterances; user override; mixed-dialect handling. | System | All | ML-STT | V3-01 | P2 | L
V3-03 | V3 | Lang Depth · Dialects | Vernacular normalization | Colloquial / numeral / date normalization | As the system, I want colloquial Bangla normalized cleanly in notes. | Local idioms, taka amounts, colloquial dates & numerals normalized in summaries. | System | All | AI-LLM | INIT-12 | P2 | M
V3-04 | V3 | Lang Depth · Interpretation | Live Bangla-English interpretation | Real-time two-way interpretation | As a user, I want live spoken translation both ways so a foreign buyer and Bangla staff can talk. | Two-way spoken translation; <2s latency; usable live; handles code-switch. | System | All | AI-LLM, ML | V1-04, V2-05 | P1 | XL
V3-05 | V3 | Lang Depth · Interpretation | Live Bangla-English interpretation | Per-speaker translated captions | As a user, I want each speaker's words shown in my chosen language. | Per-speaker translated captions with labels; toggle source/target language. | System | All | AI-LLM | V3-04, V1-14 | P2 | L
V3-06 | V3 | Lang Depth · Interpretation | Live Bangla-English interpretation | Bilingual aligned transcript export | As a user, I want a side-by-side bilingual transcript afterwards. | Aligned Bangla/English transcript; export to PDF & DOCX. | User | Professional | Backend | V3-04 | P2 | M
V3-07 | V3 | Lang Depth · Voice Agent | Bangla voice agent | Voice query — ask out loud in Bangla | As a user, I want to ask my notes questions out loud in Bangla and hear the answer. | Voice query in Bangla; grounded answer as text + spoken; conversational follow-ups. | User | All | AI-LLM, ML | V1-05 | P1 | L
V3-08 | V3 | Lang Depth · Voice Agent | Bangla voice agent | Natural Bangla text-to-speech | As the system, I want natural Bangla TTS for spoken answers & summaries. | Natural Bangla TTS; adjustable speed; intelligible on low-end speakers. | System | All | ML | V3-07 | P2 | L
V3-09 | V3 | Lang Depth · Voice Agent | Bangla voice agent | Hands-free conversational mode | As a user, I want hands-free voice access while driving or walking. | Wake-word / hands-free invoke; conversational follow-ups; safe one-hand UX. | User | All | Mobile, AI-LLM | V3-07 | P2 | M
V3-10 | V3 | Agentic · Follow-through | Auto follow-up | Auto-draft & send follow-ups | As a user, I want follow-up messages drafted and sent from meeting decisions. | Drafts from decisions; approve-then-send or auto-send via WhatsApp/email. | User | Professional | AI-LLM, Backend | V1-01, V1-10 | P1 | L
V3-11 | V3 | Agentic · Follow-through | Auto follow-up | Auto-schedule from decisions | As the system, I want a meeting scheduled when the conversation agrees to one. | Detects scheduling intent then creates a calendar event with attendees & reminders. | System | Professional | AI-LLM, Backend | V1-08 | P1 | M
V3-12 | V3 | Agentic · Follow-through | Task automation | Action-item to reminder/task automation | As the system, I want extracted action items turned into tracked reminders. | Tasks become reminders with due dates; nudges; sync to external task apps. | System | Professional | Backend | MVP-04, MVP-05 | P1 | M
V3-13 | V3 | Agentic · Follow-through | Document automation | Form & document auto-fill | As a user, I want forms/reports auto-filled from a session. | Populates a chosen template/form from session content; user reviews before save. | User | All | AI-LLM | V1-03 | P2 | L
V3-14 | V3 | Agentic · Orchestration | Agentic workflows | Custom trigger-to-action recipes | As a user, I want to automate 'if a meeting is tagged X, do Y'. | Build & save automations; template library; enable/disable per workspace. | User | Professional | AI-LLM, Backend | V3-10, V3-12 | P2 | XL
V3-15 | V3 | Agentic · Orchestration | Proactive prep | Pre-meeting briefing agent | As the system, I want a brief prepared before each meeting. | Before a calendar meeting, compiles a brief from related past sessions. | System | Professional | AI-LLM | V1-05, V1-08 | P2 | M
V3-16 | V3 | Agentic · Orchestration | Action approval | Multi-step execution with approval & audit | As a user, I want to review and approve agent actions safely. | Shows planned actions; approve/deny; full audit log of executed actions. | User | Professional | Backend, AI-LLM | V3-10, V3-11 | P2 | L
V3-17 | V3 | Ambient · Capture | Always-on ambient capture | Continuous low-power ambient recording | As a user, I want all-day passive capture so I never miss a conversation. | All-day battery-safe capture; auto-segmentation; strict privacy guardrails. | System | All | Mobile, ML-STT | INIT-08, INIT-18 | P1 | XL
V3-18 | V3 | Ambient · Capture | Always-on ambient capture | Auto conversation segmentation | As the system, I want the ambient stream split into distinct titled sessions. | Splits by speaker/topic/time-gap; auto-titles; merges fragments. | System | All | ML, AI-LLM | V3-17 | P1 | L
V3-19 | V3 | Ambient · Capture | Ambient privacy | Consent, mute-zones & retention controls | As the system, I want strong privacy guardrails for always-on capture. | Pause/mute zones; on-device-only option; consent prompts; auto-purge rules. | System | All | Mobile, Backend | V3-17, V2-12 | P0 | M
V3-20 | V3 | Ambient · Capture | Wearable support | BT mic / wearable integration | As a user, I want to pair a wearable or BT mic for cleaner ambient audio. | Pair external BT mic/wearable; battery & connection status; auto-failover to phone. | User | All | Mobile | V3-17 | P2 | L
V3-21 | V3 | Ambient · Super-Modes | Context-aware modes | Auto context detection & lens switching | As the system, I want the right template applied based on the situation. | Detects lecture vs meeting vs consultation vs field-visit; applies matching summary style. | System | All | AI-LLM | MVP-07, V1-03 | P1 | L
V3-22 | V3 | Ambient · Super-Modes | Healthcare ambient mode | Consultation lens to structured note + Rx (Niramoy) | As a doctor, I want ambient consultation capture turned into a clinical note and prescription. | Ambient consult to SOAP note + prescription draft to Niramoy/EMR export; on-device privacy. | User | Doctor | AI-LLM, Backend | V2-06, V2-07, V3-21 | P1 | XL
V3-23 | V3 | Ambient · Super-Modes | Education ambient mode | Lecture lens to notes + study pack | As a student, I want ambient lecture capture turned into a Bangla study pack. | Ambient lecture to Bangla notes + key terms + quiz/flashcards; coaching-friendly export. | User | Student | AI-LLM | V2-08, V3-21 | P2 | L
V3-24 | V3 | Ambient · Super-Modes | Personal memory | Second-brain searchable life-log | As a user, I want a searchable timeline of everything I've captured. | Chronological ambient memory; deep recall (what did X say about Y last week); privacy-scoped. | User | All | AI-LLM, Backend | V1-05, V3-17 | P1 | XL
V3-25 | V3 | Ambient · Super-Modes | Personal memory | Proactive ambient insights | As the system, I want to surface commitments and highlights from the ambient stream. | Daily highlights; surfaces promises/commitments you made; gentle, non-spammy nudges. | System | All | AI-LLM | V3-24, V2-01 | P2 | M

## Overview & Legend
Doppio — Overview & Legend
How to use this for your task list
Granularity | Each row is a buildable task (not just a feature). Promote each to a ticket; XL items should be split into subtasks during sprint planning.
Task ID | Stable ID per task (PHASE-NN). Use it to wire up Dependencies and reference tasks in your tracker.
Dependencies | Lists the Task IDs that must ship first — gives you build order within and across phases.
Acceptance Criteria | Your definition-of-done. Turn each clause into a checklist item on the ticket.
Phases
Initial | Foundation & core-tech proof: capture, Bangla STT, code-switch, storage, privacy, backend/infra.
MVP | First public, monetizable product: summaries, action items, search, Ask, Chrome ext, iOS, payments, sync, sharing.
V1 | Daily-driver depth: content generation, deep search, integrations, collaboration, team plans, diarization.
V2 | Scale & intelligence: second-brain, advanced AI, healthcare/education verticals, enterprise & ecosystem.
V3 | North-Star (game-changers): Bangla dialects & live interpretation, Bangla voice agent, agentic auto-actions, and always-on ambient capture with context super-modes.
North-Star pillars (V3)
A · Language depth | Regional dialect STT, live Bangla<->English interpretation, Bangla voice agent + TTS.
B · Agentic actions | Auto follow-ups, auto-scheduling, task & form automation, approval-gated agent workflows.
C · Ambient + super-modes | Always-on ambient capture, auto-segmentation, context lenses (healthcare/education), second-brain recall.
Persona (actor in the user story)
User | End-user actions — recording, viewing, searching, sharing, paying.
System | Automated / AI / background behaviour, no human trigger — transcription, summaries, sync, suggestions.
Admin | Management & org-level controls — team billing, analytics, access, compliance.
Surfaces (where users access Doppio)
Web portal | The central hub — access & manage everything: library, notes, search, billing, team, settings.
Mobile apps | Capture on the go (Android & iOS) plus full access.
Chrome extension | Quick on/off capture for any browser meeting; deep-links into the web portal.
Component (build layer / team)
Mobile | Android app (shared logic with iOS).
iOS | iOS-specific app work.
Chrome | Browser extension — quick on/off capture.
Web | Web portal — central hub to access & manage everything.
Backend | APIs, sync, billing logic, search index.
ML-STT | Bangla speech-to-text models & inference.
AI-LLM | Summaries, Q&A, content generation.
ML | Embeddings, diarization, other models.
Payments | bKash/Nagad/Rocket/card gateways.
Infra | Cloud, CI/CD, hosting, monitoring.
Design | UX, copy, localization review.
Effort (rough)
S | ≤ 2 days
M | 3–5 days
L | 1–2 weeks
XL | 2+ weeks — split into subtasks
Priority
P0 | Must-have to ship the phase.
P1 | Should-have; strong value, fast-follow.
P2 | Nice-to-have; opportunistic.
Task counts
Initial tasks | 21
MVP tasks | 37
V1 tasks | 21
V2 tasks | 14
V3 tasks | 25
P0 (must-have) | 34
Total tasks | 118